## Slide 1: Project Schedule Management
Sarah Mazhar

## Slide 2: Scheduling a Project Importance
Ever wondered why you create To Do list for yourself?
Ever reflected on the importance of a calendar in your life?
These lists and calendars help you plan your day to day activities
They serve as the indispensable roadmap in an unfamiliar terrain
For software project: you need a schedule to see it through smoothly

## Slide 3
It was stated earlier that there are multiple activities in a project. Here we will learn to schedule the activities.
As a PM, you need to assign durations to all the activities and monitor their progress.
Need to plan the order in which the activities will be performed as well as the start and end dates for each activity
We will learn about two tools
  Gantt Charts and
  Network Scheduling Techniques

## Slide 4: Need for Project Scheduling
Software projects have a tendency to get out of control because of the multiple activities that need to be monitored, tracked, and controlled.
When a project goes out of control, the original deadlines, the budget, and the effort required overshoot the initial estimates
This not only impacts the product, but also the credibility of the development team.

## Slide 5: What delays a project
Various reasons include
The initial estimate of the effort and resources required to complete the software project was incorrect
Changes in client requirements were not accounted for in the project schedule
Known risks were not mitigated
Technical difficulties surfaced during software product development
Human difficulties became unmanageable
The initial deadline set for the project was unrealistic

## Slide 6: How to prevent
Study similar past projects for the methods of dealing with the similar situations. Use the historical information to project time and effort estimates for the current software project.
Use an incremental process model to create a schedule to deliver the required
Present the schedule created on the basis of past projects to the client. Explain the projected delays and reasons of the same
Present the incremental model as a strategy

## Slide 7: Network Planning Models
There are many project scheduling techniques that model the project’s activities and their relationships as a network.
These include
Arrow diagramming method (ADM) also called activity on arrows
Precedence method also called Activity on nodes
Gantt chart
CPM (Critical Path Method)
PERT

## Slide 8
In all these network diagrams, the time flows from left to right
These techniques were originally developed in the 1950s
The two best-known are CPM and PERT
CPM and PERT used an activity-on arrow approach to visualize the project as a network

## Slide 9: PERT/CPM
PERT
  Program Evaluation and Review Technique
  Developed by U.S. Navy for Polaris missile project
  Developed to handle uncertain activity times
CPM
  Critical Path Method
  Developed by Du Pont & Remington Rand
  Developed for industrial projects for which activity times generally were known
Today’s project management software packages have combined the best features of both approaches.

## Slide 10: PERT/CPM
PERT/CPM is used to plan the scheduling of individual activities that make up a project.
Projects may have as many as several thousand activities.
A complicating factor in carrying out the activities is that some activities depend on the completion of other activities before they can be started.

## Slide 11: PERT/CPM
Project managers rely on PERT/CPM to help them answer questions such as:
  What is the total time to complete the project?
  What are the scheduled start and finish dates for each specific activity?
  Which activities are critical and must be completed exactly as scheduled to keep the project on schedule?
  How long can noncritical activities be delayed before they cause an increase in the project completion time?

## Slide 12: Project Network
A project network can be constructed to model the precedence of the activities.
The nodes of the network represent the activities.
The arcs of the network reflect the precedence relationships of the activities.
A critical path for the network is a path consisting of activities with zero slack.

## Slide 13: Example: Frank’s Fine Floats
Frank’s Fine Floats is in the business of building elaborate parade floats. Frank and his crew have a new float to build and want to use PERT/CPM to help them manage the project .
The table on the next slide shows the activities that comprise the project. Each activity’s estimated completion time (in days) and immediate predecessors are listed as well.
Frank wants to know the total time to complete the project, which activities are critical, and the earliest and latest start and finish dates for each activity.

## Slide 14: Example: Frank’s Fine Floats
Immediate Completion
Activity Description Predecessors Time (days)
A Initial Paperwork --- 3
B Build Body A 3
C Build Frame A 2
D Finish Body B 3
E Finish Frame C 7
F Final Paperwork B,C 3
G Mount Body to Frame D,E 6
H Install Skirt on Frame C 2

## Slide 15: Example: Frank’s Fine Floats
Project Network
Start
Finish
B
3
D
3
A
3
C
2
G
6
F
3
H
2
E
7

## Slide 16: Earliest Start and Finish Times
Step 1: Make a forward pass through the network as follows: For each activity i beginning at the Start node, compute:
  Earliest Start Time = the maximum of the earliest finish times of all activities immediately preceding activity i. (This is 0 for an activity with no predecessors.)
  Earliest Finish Time = (Earliest Start Time) + (Time to complete activity i ).
The project completion time is the maximum of the Earliest Finish Times at the Finish node.

## Slide 17: Example: Frank’s Fine Floats
Earliest Start and Finish Times
Start
Finish
3 6
B
3
6 9
D
3
0 3
A
3
3 5
C
2
12 18
G
6
6 9
F
3
5 7
H
2
5 12
E
7

## Slide 18: Latest Start and Finish Times
Step 2: Make a backwards pass through the network as follows: Move sequentially backwards from the Finish node to the Start node. At a given node, j, consider all activities ending at node j. For each of these activities, i, compute:
  Latest Finish Time = the minimum of the latest start times beginning at node j. (For node N, this is the project completion time.)
  Latest Start Time = (Latest Finish Time) - (Time to complete activity i ).

## Slide 19: Example: Frank’s Fine Floats
Latest Start and Finish Times
Start
Finish
3 6
6 9
B
3
6 9
9 12
D
3
0 3
0 3
A
3
3 5
3 5
C
2
12 18
12 18
G
6
6 9
15 18
F
3
5 7
16 18
H
2
5 12
5 12
E
7

## Slide 20: Determining the Critical Path
Step 3: Calculate the slack time for each activity by:
Slack = (Latest Start) - (Earliest Start), or
= (Latest Finish) - (Earliest Finish).

## Slide 21: Example: Frank’s Fine Floats
Activity Slack Time
Activity ES EF LS LF Slack
A 0 3 0 3 0 (crit.)
B 3 6 6 9 3
C 3 5 3 5 0 (crit.)
D 6 9 9 12 3
E 5 12 5 12 0 (crit.)
F 6 9 15 18 9
G 12 18 12 18 0 (crit.)
H 5 7 16 18 11

## Slide 22: Example: Frank’s Fine Floats
Determining the Critical Path
  A critical path is a path of activities, from the Start node to the Finish node, with 0 slack times.
  Critical Path: A – C – E – G
  The project completion time equals the maximum of the activities’ earliest finish times.
  Project Completion Time: 18 days

## Slide 23: Example: Frank’s Fine Floats
Critical Path
Start
Finish
3 6
6 9
B
3
6 9
9 12
D
3
0 3
0 3
A
3
3 5
3 5
C
2
12 18
12 18
G
6
6 9
15 18
F
3
5 7
16 18
H
2
5 12
5 12
E
7

## Slide 24: Example: ABC Associates
Earliest/Latest Times and Slack
Activity ES EF LS LF Slack
A 0 6 0 6 0 *
B 0 4 5 9 5
C 6 9 6 9 0 *
D 6 11 15 20 9
E 6 7 12 13 6
F 9 13 9 13 0 *
G 9 11 16 18 7
H 13 19 14 20 1
I 13 18 13 18 0 *
J 19 22 20 23 1
K 18 23 18 23 0 *

## Slide 25: Example: ABC Associates
Determining the Critical Path
  A critical path is a path of activities, from the Start node to the Finish node, with 0 slack times.
  Critical Path: A – C – F – I – K
  The project completion time equals the maximum of the activities’ earliest finish times.
  Project Completion Time: 23 hours

## Slide 26: Practice
Now we will make the network according to the table.